## PBlist
PROJECT BACKLOG
10 | = highest Reference ID number
引用编号 | 版本 | 冲刺号 | 分类 | 标题 | 故事 | 类型 | 进度 | 初始估计（h） | 优先级 | 如何演示 | 商业价值 | 理想时间（h） | 调整因子 | 复杂度 | 信息度 | 备注
1 | 1 | 1 | user story | 签到 | 作为一个经常读书的书友，自然希望自己每天都欧气满满，决不允许自己一日不读书，书中自有黄金屋，签到，是每个热爱图书的人的必选。 | Initial Feature | Not Done | 3 | 99 |  |  | 3
2 | 1 | 1 | user story | 收藏图书 | 作为一个书友好看的图书怎么能只看一次就够呢，书读千遍，其义自见，只是一两次简单的领略完全不足以体现书的价值，为了防止找不到最爱的书，我要收藏图书。 | Initial Feature | Not Done | 2 | 97 |  |  | 2
3 | 1 | 1 | user story | 分享 | 作为一个书友，自己一个人看书实在感觉少了点什么，独乐乐不如众乐乐，我想把自己看过的图书也能分享给我的朋友，一起欢笑一起乐。 | Initial Feature | Not Done | 3 | 94 |  |  | 3
4 | 1 | 1 | user story | 图书分类 | 作为运营商，为了方便用户查看自己喜欢的图书，自然要对图书进行分门别类，同时也方便我们管理图书。 | Initial Feature | Not Done | 2 | 92 |  |  | 2 | 0
5 | 1 | 1 | user story | 榜单 | 作为一个书友，茫茫无所是从不知道做什么的时候，希望有一个远洋中的风帆，指点迷津，这个时候，榜单自然是最重要的。 | Initial Feature | Not Done | 3 | 91 |  |  | 3
6 | 1 | 1 | user story | 完结 | 作为一个书友，但是又繁忙与各种生活琐事之间，少有的闲暇时间自然不想被没有完结的图书所打断，要看就要看的尽兴，完结的图书自然是不二之选。 | Initial Feature | Not Done | 2 | 90 |  |  | 2
7 | 1 | 1 | user story | 生活励志 | 作为一个书友，不能仅仅陷入网络的虚拟之中，我希望从书中获取知识，为自己的生活增添几分积极向上的气息，励志小说我也蛮喜欢的。 | Initial Feature | Not Done | 3 | 89 |  |  | 3 | 0
8 | 1 | 1 | user story | 高能Hi聊 | 作为一个书友，看到喜悦之处却无人Hi聊实在是太过蓝瘦，如果能够和网友们一起侃侃而谈，讨论这芸芸众生实在是秒哉。 | Initial Feature | Not Done | 2 | 86 |  |  | 2
9 | 1 | 1 | user story | 创作 | 作为运营商，希望更多的人能够参与到图书的发展之中，希望能出现更多的平民作家，更多人的投入有助于图书的友好发展。 | Initial Feature | Not Done | 5 | 83 |  |  | 5 | 0
10 | 1 | 1 | user story | 记录账号密码 | 作为一个书友，每次都要输入手机号和密码实在太麻烦了，能够记录账号密码实在是方便至极。 | Initial Feature | Not Done | 2 | 80 |  |  | 2
27
1 | 2 | 2 | user story | 搜索 | 作为一个书友，我希望可以快速找到自己喜欢的图书 | Initial Feature | Not Done | 3 | 56 |  |  | 3
2 | 2 | 2 | user story | 评论 | 作为运营商，防止有些戾气太重的过激言论扰乱读书风气 | Initial Feature | Not Done | 1 | 50 |  |  | 1 | 0
3 | 2 | 2 | user story | 点赞 | 作为一个书友，我希望给自己喜欢的发言点个赞，以表达出我内心的真挚感情 | Initial Feature | Not Done | 1 | 45 |  |  | 1 | 0
4 | 2 | 2 | user story | 数据库保密 | 作为运营商，要防止自己的数据泄密，运用md5加密技术，为用户的信息保驾护航 | Initial Feature | Not Done | 3 | 43 |  |  | 3
5 | 2 | 2 | user story | 防止二次注册 | 作为一个运营商，绝对不允许一个手机号多次注册，否则会引起混乱 | Initial Feature | Not Done | 1 | 40 |  |  | 1
6 | 2 | 2 | user story | 意见反馈 | 作为一个发烧书友，对于自己新的一些想法希望能够反馈给官方，因此希望有个意见反馈界面 | Initial Feature | Not Done | 1 | 35 |  |  | 1
10
Total |  | 16 | [5 empty] | 74
Generate index cards
Note on A4: Luc Segers: This is the highest reference ID number used so far.
Note on A5: Luc Segers: This reference ID should be unique. This number is used throughout the whole worksheet so be aware.
Note on B5: Luc Segers: This is the release where the story will be developped
Note on C5: Luc Segers: This is the sprint where the story will be developped
Note on D5: Luc Segers: This is a category to which the story belongs. Example : Infrastrucuture, Back-End, Animation, ...
Note on F5: Luc Segers: This is the story (Feature, Epic, User). Depending on in which phase you are in (Présales, Scope, …) the detail could be higher. Normally you could describe a user story as follow: As a <Role> I can do <this> and the result is <that> ... Offcourse this is not always possible, so you should be creative. A story should conduct to the following rules: I = Independent N = Negotiable V = Valuable to customer E = Estimatable S = Small T = Testable
Note on G5: Luc Segers: Type of the story.
Note on H5: Luc Segers: Status of the story
Note on I5: Luc Segers: This column is calculated: Ideal Hours * Adjustment Factor
Note on J5: Luc Segers: M = Must Have S = Should Have C = Could Have W = Won't have this time
Note on L5: Luc Segers: 0 = Lowest Business Value 100 = Highest Business Value
Note on M5: Luc Segers: Enter here the new ideal estimates which are done with planningpoker
Note on N5: Luc Segers: This column is calculated based on the values of complexity and information. The data is looked up in the setup tab.
Note on O5: Luc Segers: Complexity 0 = Not Defined 1 = Very Simple 2 = Simple 3 = Moderate 4 = Complex 5 = Extreme Complex
Note on P5: Luc Segers: Information 0 = Not Defined 1 = No information 2 = Little information 3 = Moderate information 4 = Much information 5 = All information
Note on C24: Luc Segers: Total amount of stories available in the project backlog
Note on I24: Luc Segers: total amount of estimated hours

## ChongCi1
[5 empty] | Total Remaining |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| TODAY: | 2018-12-28 |  |  | Ideal Curve |  | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
| SPRINT NAME: | ChongCi1 | [5 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
| # Days / Sprint: | #N/A | Total Baseline Hours : |  | 0 | Remaining : | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
备录标题 | 冲刺备录项 |  | 责任人 | 状态 | 预期 | 剩余 | 底线 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
图书分类 | 作为运营商，为了方便用户查看自己喜欢的图书，自然要对图书进行分门别类，同时也方便我们管理图书。 | 前端界面 | 李元彪 | Done
|  | 后台实现 | 白凯发
|  | 数据库管理 | 杨影 | Done
榜单 | 作为一个书友，茫茫无所是从不知道做什么的时候，希望有一个远洋中的风帆，指点迷津，这个时候，榜单自然是最重要的。 | 前端界面 | 王雪宾
|  | 后台实现 | 孙晓雪
完结 | 作为一个书友，但是又繁忙于各种生活琐事之间，少有的闲暇时间自然不想被没有完结的图书所打断，要看就要看的尽兴，完结的图书自然是不二之选。 | 前端界面 | 杨世佳 | Done
|  | 后台实现 | 杨影
|  | 数据库管理 | 孙晓雪
高能Hi聊 | 作为一个书友，看到喜悦之处却无人Hi聊实在是太过蓝瘦，如果能够和网友们一起侃侃而谈，讨论这芸芸众生实在是妙哉。 | 前端界面 | 高晓刚 | Done
|  | 后台实现 | 白凯发
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## ChongCi2
备录标题 | 冲刺备录项 |  | 责任人 | 状态 | 预期 | 剩余 | 底线 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
搜索 | 作为一个书友，我希望可以快速找到自己喜欢的图书 | 前端界面 | 王雪宾 | Done
|  | 后台实现 | 白凯发
评论 | 作为运营商，防止有些戾气太重的过激言论扰乱读书风气 | 前端界面 | 李元彪
|  | 后台实现 | 孙晓雪
点赞 | 作为一个书友，我希望给自己喜欢的发言点个赞，以表达出我内心的真挚感情 | 前端界面 | 杨世佳
|  | 功能实现 | 白凯发
|  | 后台实现 | 杨影
|  | 数据库管理 | 李元彪
数据库保密 | 作为运营商，要防止自己的数据泄密，运用md5加密技术，为用户的信息保驾护航 | s | 高晓刚
|  | 后台实现 | 白凯发
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0